Copy ___ of ___ Copies

Joint Force Headquarters Tennessee National Guard

Nashville, TN

GFS012

FRAGORD 3 to JFHQ-TN OPORD 25-18 (Tennessee Maneuvers 2026 (TNMAN 26)) (UNCLASSIFIED)

(U) References:

- JPUB 5-0 Joint Planning (JUL 2024)

- JFHQ-TN OPORD 25-07 DOMOPS BASE ORDER (FEB 2025)

- Tennessee Emergency Management Plan (FEB 2024)

- Tennessee State Hazard Mitigation Plan (AUG 2023)

- AR 380-5 Army Information Security Program (MAR 2022)

(U) Time Zone Used Throughout the PLAN: Central Standard Time / Sierra

(U) Task Organization: TBP

1. (U) Situation. N/C

2. (U) Mission.  N/C

3. (U) Execution.

3.A. (U) Commander’s Intent. N/C

3.B. (U) Concept of Operations.

3.B.1 (U) Timeline: ///CHANGE///

| Event | Date | Location | Audience |
| --- | --- | --- | --- |
| Concept & Development Meeting | 16 JUL 2025 | JFHQ – JOC | J3/DOMS FTSP and TEMA |
| TNNG TNMAN Sync | 11 SEP 2025 | JFHQ – JOC | J3/DOMS FTSP, TNNG, and TEMA |
| Initial Planning Meeting | 28-29 OCT 2025 | JFHQ-TEMA | J3/DOMS, TNNG Trusted Agents, TEMA, Partners |
| Mid Planning Meeting | 11-12 DEC 2025 | TEMA East Region Office |  |
| Final Planning Meeting | 26-27 MAR 2026 | JFHQ-TEMA* |  |
| TNMAN 26 Exercise | 13-17 MAY 2026 | Statewide |  |

*Note: Virtual meeting will be available and sent along with the TNMAN 26 FPM LOI.

3.C. (U) Task. ///CHANGE///

3.C.1. (U) Tasks to Staff. No Change

3.C.2. (U) Tasks to Subordinate Units. ///CHANGE///

3.C.2.A. (U) TNARNG. ///CHANGE///

3.C.2.A.1. (U) 30th TC. ///CHANGE///

3.C.2.A.1.A. (U) Provide 6 PAX to White Cell during TNMAN 26 exercise, 11-17 MAY. Duty location JFHQ.

3.C.2.A.2. (U) 278th ACR. ///CHANGE///

3.C.2.A.2.A. (U) ///ADD/// Provide space  for 50 individuals within the Mt Carmel Armory (399 Highway 11W, Mt Carmel, TN 37645) to be utilized as a RON and ICP location for the duration of TNMAN 26 (11-17 MAY 26) IOT support JTF Security and COMMS Operations.

3.D. (U) Coordinating Instructions. ///CHANGE///

3.D.2.A. (U) Provide name, rank, military email and phone number of any Trusted Agents or Players NLT 18 MAR 2026. to MAJ Trint Callison trinity.r.callison.mil@army.mil, MAJ Kristin Crandall kristin.k.crandall.mil@army.mil, and 2LT Gabriel Sussman, gabriel.f.sussman.mil@army.mil.

4. (U) Administration and Logistics. N/C

5. (U) Command and Control. N/C

5.A. (U) Command. N/C

5.B. (U) Control.

5.B.1. (U) Primary POC for this order is MAJ Trint Callison, Deputy DOMS, trinity.r.callison.mil@army.mil or (615) 417-9811.

5.B.2. (U) Alternate POC for this order is MAJ Kristin Crandall, Plans and Operations Officer, Kristin.k.crandall.mil@army.mil or (615) 939-2252.

5.C. (U) Joint Communication Support. N/C

ACKNOWLEDGE:

ROSS

MG

OFFICIAL:

Lowrance

J3

ANNEXES: TBP

DISTRIBUTION: B, D, P.