COPY ___ OF ___

3 RGT, TNSG

Greenville, TN

102100RAPR26

SUMMARY: (U) Provides advanced notice for unit training and administration involving Tennessee Maneuver Exercise 2026 (TNMAN-26). Edits and changes to previously assigned tasks or narrative remain in effect until edited, changed, or completed.

(U) References:

          - WO 1 To DIV OPORD 26-05 (TNMAN 26)

          - BG Stewart email Mar 30, 2026, 2:32 PM.

          - RGT WARNO 26-05-01 TNMAN-26, dtd 112100RFEB26.

(U) Time Zone Used Throughout the OPORD: ROMEO

            - Situation. See ENCL A: RO 26-05-01 HDWG TNMAN-26 Overview.pptx

            - Area of Interest.  The states comprising FEMA Region 4 (AL, FL, GA, KY, MS, NC, SC, and TN.); VA; AR, and MO, and the Mississippi River.

            - Area of Operations.  The 26 counties that comprise TEMA East Region; Volunteer Training Site – Tullahoma (VTS-T); Volunteer Training Site – Smyrna (VTS-S); Volunteer Training Site – Milan (VTS-M); and Home Station / Drill Locations.

- Holston Army Ammunition Plant. This government-owned, contractor-operated ammunition and explosives plant is the largest capacity supplier of high performance explosives in the country. The current plant is on two sites: Plant A is at 4509 W Stone Dr, Kingsport, TN 37660 (Sullivan County). Plant B is about 4 miles (6.4 km) east in a less developed part of Hawkins County. The two plants are connected by rail. Plant A has 120 acres (0.49 km2). Plant B has 5,900 acres (24 km2). The site (Plants A and B) includes ~ 465 buildings.

            - Enemy Forces.  UNK.

            - Friendly Forces.  TNSG / TNNG / TEMA / Local Emergency Departments / Local Law Enforcement / TN Highway Patrol / multiple supporting states / Federal, State, and local agencies.

            - Interagency, Intergovernmental, and Nongovernmental Organizations. The TEMA Eastern Regional office is established to improve services to the local emergency management directors and agencies of the several counties. Services include technical guidance, information on federal and state requirements for emergency management, updates on law and regulations, technical advice on grants, National Incident Management System (NIMS) and other reports required for federal funding, information on other training, and a rapid avenue to submit requests for state or other external mutual aid or assistance. Major Hazards include: Several nuclear power, research, fuel or weapons facilities, wildland or forest fires, flooding, hazardous materials, severe weather, and earthquakes.

            - Civil Considerations. TBD.

            - Assumptions. TBD.

            - Mission.

- 3 RGT participates in DIV training operations in the Tennessee Maneuver Exercise 2026 (TNMAN-26) (Simulated Kinetic Attack Holston Ammunition Plant) in multiple locations across TN 12-17 MAY 26 in order to (IOT) increase MET proficiency, sustain collective and staff training proficiency at the Regimental level.

            - EXECUTION.

- Initial Commander’s Intent.  This order is to synchronize the efforts of all units throughout the Regiment IOT maintain and improve the readiness and METL based training and Command and Control during IDT and prepare for TNMAN-26.

- Concept of Operations.

- During TNMAN-26, 3 RGT will work with TNSG / TNNG / TEMA / Local Emergency Departments / Local Law Enforcement / TN Highway Patrol / multiple supporting states / Federal, State, and local agencies to support the TNMAN-26 (Simulated Kinetic Attack at Holston Ammunition Plant Scenario Operations). The decisive operation is SECFOR Operations: Area security, Dismounted and Aerial Patrols, Traffic Control Points (TCPs), and Surveillance of the maritime domain (Holston River) and Radio Communications (600 / 100 Watt) conducted in multiple locations across the AO.

- This operation will be conducted in three phases.

- (U) Phase I: Planning and Coordination. This phase begins with the receipt of Warning Order #1 to DIV OPORD 26-05 (TNMAN-26), 111100RFEB26. It consists of planning, interagency and unit coordinating actions, and notifications to support tasks and actions during Phase II: Training Execution. This phase ends with the receipt of tasking from authorized unit and agency representatives which initiate exercise training actions no later than (NLT) 120800RMAY26.

- (U) Phase II: Training Execution. This phase begins with the receipt of tasking from authorized unit and agency representatives which initiate exercise training actions NLT 120520RMAY26 (BMNT). It consists of, but is not limited to, actions which alert, mobilize, and assemble TNSG personnel, resources, and capabilities at an Incident Command Post (ICP) or Resource Staging Area in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645, no later than 130519RMAY26 (BMNT). The 3 MP BN is the Focus of Main Effort (FOME) for this phase and is supported by 2 MP BN, 4 MP BN, HHC 3 RGT, and other supporting agencies and units. 3 MP BN has the Priority of Support (POS), followed by HHC 3 RGT, 2 MP BN, and 4 MP BN respectively. FOME and POS remain in effect until changed as necessary and directed by the CDR / ICP. This phase ends with the notification to end the exercise (ENDEX) and to demobilize the assembled TNSG personnel, resources, and capabilities NLT 132131RMAY26 (EENT).

- (U) Phase III: Recovery and AAR. This phase begins no earlier than (NET) 132131RMAY26, the end of Phase II: Training Execution. It consists of actions required to safely, efficiently, and effectively return TNSG personnel, resources, and capabilities to respective Home of Record, Home Station, and assigned units and to a state of preparedness / readiness to respond to contingency / emergency events (if needed). It also includes post-exercise activities such as Hot Wash, After Action Review and Reporting, and Corrective Action Planning and Programming in preparation for the next training event. While initial actions during this phase will most likely be completed within ~+24 Hrs of ENDEX (NLT 142131RMAY26) the post-training administrative actions may potentially be completed +90 Days of ENDEX (~ 10AUG26).

- Tasks to Subordinate Units.

- 2 MP BN.

- (U) Task 1: Be prepared to (BPT) provide personnel support to the ICP in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 NLT 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 2: BPT provide personnel and resource support to operations of small Unmanned Aerial Systems (sUAS) that are assigned to reconnaissance and detection tasks in vic Holston Army Ammunition Plant, 4509 West Stone Drive, Kingsport, TN 37660-1048 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 3: Conduct route and convoy planning to / from Home Station and the Resource Staging Area (RSA) in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 to be executed between 12 MAY 26 and 15 MAY 26. This planning and execution must be IAW applicable TNSG guidance and safety protocols. BPT brief the 3 RGT CDR regarding this plan, NLT 302100RAPR26.

- 3 MP BN.

- (U) Task 1: BPT provide personnel support to the ICP in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 2: BPT provide personnel support to SECFOR Operations in vic Holston Army Ammunition Plant, 4509 West Stone Drive, Kingsport, TN 37660-1048 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 3: BPT provide personnel and resource support to operations of small Unmanned Aerial Systems (sUAS) that are assigned to reconnaissance and detection tasks in vic Holston Army Ammunition Plant, 4509 West Stone Drive, Kingsport, TN 37660-1048 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 4: Conduct route and convoy planning to / from Home Station and the Resource Staging Area (RSA) in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 to be executed between 12 MAY 26 and 15 MAY 26. This planning and execution must be IAW applicable TNSG guidance and safety protocols. BPT brief the 3 RGT CDR regarding this plan, NLT 302100RAPR26.

- 4 MP BN.

- (U) Task 1: BPT provide personnel support to the ICP in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 2: BPT to provide an FAA Sect. 107 certified UAS pilot to coordinate and support operations of small Unmanned Aerial Systems (sUAS) that are assigned to reconnaissance and detection tasks during the TNMAN-26 Exercise NLT 120800RMAY26.

- (U) Task 3: Conduct route and convoy planning to / from Home Station and the Resource Staging Area (RSA) in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 to be executed between 12 MAY 26 and 15 MAY 26. This planning and execution must be IAW applicable TNSG guidance and safety protocols. BPT brief the 3 RGT CDR regarding this plan, NLT 302100RAPR26.

- HHC.

- (U) Task 1: BPT provide personnel support to the ICP in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 2: BPT provide personnel and resource support for the establishment and operation of a Resource Staging Area (RSA) in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 no later than (NLT) 120800RMAY26 in support of TNMAN-26 Exercise.

- (U) Task 3: Conduct route and convoy planning to / from Home Station and the Resource Staging Area (RSA) in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 to be executed between 12 MAY 26 and 15 MAY 26. This planning and execution must be IAW applicable TNSG guidance and safety protocols. BPT brief the 3 RGT CDR regarding this plan, NLT 302100RAPR26.

- (U) S1.

1. (U) Task 1: Provide a roster of personnel committed to training in the TNMAN-26 Exercise IOT facilitate Troop-to-Task organization, staffing, and MET mission sets, NLT 152000RAPR26.

2. (U) Task 2: Coordinate personnel reporting requirements with DIV G1 to support TNMAN-26, no later than 152000RAPR26.

3. (U) Task 3: Provide Regimental Orders to personnel participating in TNMAN-26 to respective subordinate units NLT 302000RAPR26 IOT enable employees to coordinate absence from employment prior to the order period (13-15 MAY 26).

4. (U) Task 4: During TNMAN-26, track personnel names and attendance location and provide daily updates to CDR and S3 during scheduled reporting periods and as needed IOT facilitate situational awareness and support incident planning.

5. (U) Task 5: BPT account for attachment of personnel from adjacent and higher units NET 120800RMAY26 IOT provide resources and capabilities for enhanced response during TNMAN-26.

- (U) S2.

1. (U) Task 1: Coordinate with DIV G2 to establish reporting requirements and IOT provide an IPB and SA briefs in support of the Incident Command Post reporting requirements and Planning purposes.

- (U) S3.

1. (U) Task 1: During TNMAN-26, BPT coordinate with external agency partners for operational support and training, to include but not limited to TEMA / TNNG.

2. (U) Task 2: Provide initial estimate of Task Force Organization Structure IAW ICS protocols IOT facilitate troop-to-task planning and coordination.

3. (U) Task 3: Contact and coordinate with Mr. Tony Armstrong, HAAP POC, at 423-341-5840 IOT coordinate TNSG exercise participation.

4. (U) Task 4: Contact and coordinate with MAJ Trinity Callison, TNNG DJ3/5/7, exercise planner IOT coordinate TNSG exercise participation.

5. (U) Task 5: Prepare a list of personnel, resources, and capabilities, required to perform the assigned mission during TNMAN-26 (12-17 MAY 26) IOT request support from DIV and adjacent units.

6. (U) Task 6: Prepare a Time Phased Force Deployment Data (TPFDD) as a planning tool used to organize, synchronize, and execute deployment / redeployment of TNSG personnel, resources, and capabilities to / from the RSA in vic US Army Reserve Center, 399 US-11W Scenic, Mt Carmel, TN 37645 NLT 302100RAPR26.

- (U) S4.

1. (U) During TNMAN-26, BPT establish a feeding, billeting transportation plan ICW DIV MOB Cell, DIV G4, and supporting agencies to include but not limited to TEMA / TNNG.

- (U) S6.

1. Prior to and during TNMAN-26, in coordination with DIV G6, receive SOI with callsigns NLT 302000RAPR26.

2. During TNMAN-26, in coordination with DIV G6, publish Signal Annex with HF / VHF frequencies and callsigns NLT 302000RAPR26.

- Coordinating Instructions.

- Units BPT to submit Unit Closing Reports upon return to Home Station and verification that unit personnel have safely returned to Home of Record.

- Units review the Serious Incident Reporting requirements and protocols.

            - Sustainment.  TBD.

            - Command and Control.  TBP.

ACKNOWLEDGE:

ROARK

COL

OFFICIAL:

SHEAF

S3

ANNEXES: N/A.

ENCLS:

A - RO 26-05-01 HDWG TNMAN-26 Overview.pptx

DISTRIBUTION:

2 MP BN

3 MP BN

4 MP BN

HHC / Staff, 3 RGT